## Slide 1
FlexForum Steering Group
Meeting agenda and context
12 February 2026
Notes: Materials shared: Monday 9 February 2026

## Slide 2: Agenda: 12 February 2026
Welcome
Strategic items
2026 action and delivery options
Standing items
Engagement
Workplan
Finance
Procedural items
Membership
Actions
Next meeting
AoB/Close

## Slide 3: 1 Welcome
Purpose of this item:
Welcome
Apologies
Reminders
Interests
Confirm the agenda
You should all be familiar with the requirements of the Commerce Act 1986, prohibiting anti-competitive conduct. You should not discuss commercially sensitive areas of competitive activity, including (but not limited to) relating to agreements to fix, control or maintain prices, restrict output or capacity, or allocate markets or customers
A written record of the discussions today will be available on the FlexForum webpage.
As steering group members you are acting in an individual capacity not as a representative of your organisation.
The purpose of the FlexForum is to support coordinated and collaborative action to make it easier for households, businesses and communities to maximise the value of consumer and distributed energy resources and flexibility to:
support affordable and reliable operation of the electricity market and power system
enable accelerated electrification by households and businesses as part of the transition in Aotearoa New Zealand to zero emissions economy

## Slide 4: 2 2026 action and delivery options (1)
Purpose of this item: to discuss the actions FF can take to deliver its objectives and priorities in 2026.
Context… several opportunities for FF to advance its objective and priorities emerged over summer
specific support of the Scaled DF project… EECA has identified 2 areas which would benefit from FF input/assistance under the support contract.
  assisting to triage and resolve technical issues faced in developing capability/project design, eg, comms functionality, data requirements, Tx and Dx pricing interaction, range of retail propositions, with a particular focus on including critical partners. Activity is expected to involve a series of technical workshops.
  assisting to streamline coordination of sectoral involvement/input to project design and delivery, eg, coordinating involvement of retailers across the suite of projects. Activity is expect to involve workshops, regular project updates and webinars.
the Electricity Authority 2026 flex programme is being developed… with initiatives being considered that would be delivered/complemented by existing/planned FF activities.
  providing enhanced flex information, particularly by increasing price (for flex) information
  reducing the cost/complexity of participation, eg, by standardising flex contracts, simplifying exemptions/sandboxing and clarifying roles of aggregators
  strengthening (network) pricing signals, including checking if pricing principles are fit for purpose
  encouraging networks to enhance price signals of emerging capacity constraints to better incentivise flex responses (and investments), to more explicitly consider flex options in asset plans and to show that flex options have been sought.
ERGANZ wants to provide its members with insights/advice on initiatives involving flex that could enhance consumer care in New Zealand. The task is aligned with an already underway scan of flexibility propositions being completed by a FF Member, and the wider look at pricing and orchestration mechanisms.
  for advice on the merits of international approaches to flexible retail propositions in the New Zealand context and whether these could be adopted in a way that benefits vulnerable and low-income customers drawing on a global scan of customer experience and insights of FF Members and associates and their relevant case studies in other markets.
  …subject to the findings further collaboration is possible, including on piloting/testing propositions.
Transpower Te Kanapu / Future grid planning… the size (and cost) of the future grid depends on the amount of flex available for deployment. Two components of the work are:
  …developing/collating robust assumptions about flex volumes, sources, price points, timing etc
  …identifying the critical enablers of more flex (a necessary condition of an efficient future grid)
a flex research collaboration could be achieved by bringing together Ara Ake, FF universities, EECA and other learners (the scaled pilots and beyond)... at this point there are multiple complementary, yet unconnected efforts.
Notes: F

## Slide 5: 2 2026 action and delivery options (2)
Each of these opportunities would help to accelerate FF efforts to advance its objective and priorities…
this table arranges the opportunities/activities listed on page 4 according to FF’s 4 activity areas and notes the expected impact/benefit
 | Flex Plan progress assessment | Deep dives | Knowledge sharing | Support for learning-by-doing
…triaging/resolving technical design/delivery issues encountered in the Scaled DF pilots (and others) |  |  | YES…joining dots | YES…joining dots
…streamlining sectoral involvement/input to Scaled DF pilot project design and delivery (and others) |  |  | YES…joining dots | YES…joining dots
…enhanced flex information, particularly by increasing price (for flex) information | YES…more flex measures |  |  | YES…measurement
…reducing the cost/complexity of participation, eg, standardising flex contracts |  |  | YES…emerging practice | YES…explores solutions
…enhancing Dx price signals to better incentivise flex responses (and investments) etc |  | YES…how? |  | YES…testing options
…advice on the merits of international approaches to flexible retail propositions to benefit vulnerable and low-income customers |  | YES… aspect of pricing/orchestration Qs | YES | YES…testing options
…developing/collating robust assumptions about flex volumes, sources, price points, timing etc |  |  | YES | YES… providing evidence
…identifying the critical enablers of more flex | YES |  |  | YES…priorities
…flex research collaboration | YES |  | YES | YES…more/cheaper
Notes: F

## Slide 6: 2 2026 action and delivery options (3)
FF resources are currently insufficient to fully take advantage of these opportunities … we need extra dedicated bodies and/or extra funding to pay them
Note: the option to not fully take advantage of these opportunities is available, but is not being considered until all avenues for accelerating FF objectives and priorities have been exhausted.
Actions: Identify plausible human and funding options to fully take advantage of these opportunities.
Notes: F

## Slide 7: 3 Engagement (1)
Purpose of this item:
conversations had and upcoming
advice to regulators
publicising FF activities and thinking
update on who is listening to FlexForum through its website, newsletter and linkedin channels
Conversations had and upcoming
IEGA on 11 February discussing IEGA and FF activities
Electricity Authority- on 5 February discussing FF activities and EA thinking on next steps (see item 2 for more detail)
Gabrielle Kuiper (leading Australian thinker on DER) on 30 January discussing FF and intersections with their research. A FF webinar will be arranged for Gabrielle to share insights/practice from Australia and southeast Asia.
Transpower Te Kanapu team on 29/01 and 05/02… 2-part workshop on flex assumption inputs for the draft future grid blueprint. A follow up session is planned after release of final scenarios (March).
ERGANZ on 21 January discussing FF activities and ERGANZ flex interests/plans (see item 2 for more detail).
workshop hosted for Transpower WBOP team on 20/02. 20 people attended. Here are the session notes.
Energy Transition Framework secretariat and Transpower on 13 January discussing adding flex measures to the ETF Measures and Metrics report. (See item 4 for more detail.)
Next ETF meeting is 6 March…the draft agenda includes:
  Powering change campaign update/plans
  Update on implementation of Gas working group actions
  Review of proposals on Removing finance related barriers to C&I electrification
  Workforce for the future update
Actions: For noting. No actions requested.
Notes: FNF work programme
connection queue management - a single ENA-managed queue policy ranking and sorting (EA requirement)
network data stocktake - baseline of existing data, standardised MVP data specifications and roadmap consistency
capacity maps - EDB hosting capacity model, planning time maps (today v 5 years time headroom)
INTSA process development guidance - cross-EDB portal for sharing innovation projects and applications experience
valuing NTS - framework to value flexibility, capex deferral and non-traditional solutions
dynamic capacity allocation - prove real time hosting calculation, DOE standard and LV/EV/HW + HV congestion management
a load management protocol - a common set of terms for how retailers and EDBs coordinate their load management activities in instances of network and grid emergencies.

## Slide 8: 3 Engagement (2)
Advice to regulators
no responses to regulatory consultations are being prepared.
Publicising FF activities and thinking… FF content is shared regularly when it is available.
we shared this article on 15 January about FF estimates of the scale and capability of flexible resources already deployed ‘in the system’.
we acknowledged on 28 January the EECA report on estimates of potential flex.
Actions: For noting. No actions requested.
Notes: FNF work programme
connection queue management - a single ENA-managed queue policy ranking and sorting (EA requirement)
network data stocktake - baseline of existing data, standardised MVP data specifications and roadmap consistency
capacity maps - EDB hosting capacity model, planning time maps (today v 5 years time headroom)
INTSA process development guidance - cross-EDB portal for sharing innovation projects and applications experience
valuing NTS - framework to value flexibility, capex deferral and non-traditional solutions
dynamic capacity allocation - prove real time hosting calculation, DOE standard and LV/EV/HW + HV congestion management
a load management protocol - a common set of terms for how retailers and EDBs coordinate their load management activities in instances of network and grid emergencies.

## Slide 9: 3 Engagement (3)
Update on website, newsletter and linkedin channel traffic during January 2026
Website users, sessions and views were healthy for a January. Traffic is strongly correlated with LinkedIn posts and the newsletter…. People want to know about FF events and what it thinks
Knowledge Hub data being included in future reports… most popular section is Learning project updates
No public newsletter in January. But used mailchimp for 2 fortnightly flashes…
Friday 16/01 = 29.6% unique open rate
Friday 30 January = 25.2% unique open rate
FF was not busy on the socials in January (2 posts) but LinkedIn follower numbers continue to increase (now 624). The post of the month was on 29/01 sharing our take on the EECA research on the scale of flex potential

## Slide 10: 4 Workplan (1)
Purpose of this item: an update on progress with FlexForum tasks/activities across 4 areas.
Flexibility Plan progress assessment
Deep dives to provide a FF view (‘vision’) on foundational issues/topics
Knowledge sharing
Support for learning-by-doing
No other party is undertaking equivalent tasks (that we know of).
Flexibility plan progress assessment. This is a must-do task required by the FF constitution. The 2026 focus is assessing and reporting progress.
activity is required March-May to produce the (3rd) progress report ahead of the 2026 AGM in July/August.
experience suggests that Member input is most easily (for them) and effectively obtained via workshops/structured discussions.
The progress report can include quantitative progress measures by using early (‘experimental’) metrics produced by Transpower for the ETF.
Deployed and potential flexible capacity reported in MW using FF estimates for 2025 and 2030. Metric gives an one-off indicative snapshot of available and potential flex
  Presented as a one-off standalone measure with commentary on the existing generation pipeline noting that flexible resources may help bridge supply gaps
Potential demand-side flexibility using EECA modelling. Metric gives a one-off indicative snapshot of how much electricity demand could be shifted away from peak periods under different uptake and incentive assumptions, and how this potential evolves through to 2040.
  Presented as supporting context illustrating the potential scale and role of demand-side flexibility in future system operation.
Aggregate distributed stationary battery storage reported in MW using MBIE data on residential solar installations with battery storage. Metric gives an ongoing indication of household-level battery capacity available to provide flexibility.
Flex data is incomplete, but the EA has detailed data on flex contracted by retailers
Transpower observes that existing data is ambiguous and incomplete. System-wide flexibility data is not yet available through a single, comprehensive public dataset. Much of the required data is held across multiple organisations and is not collected in a consistent or centralised way. Desirable data (MW and MWh) = number of ICPs providing water heating flexibility; C&I flex; EV charging; and EV batteries
BUT. Data available via the EA retail market monitoring notice (monthly from 01-25) includes: # resources/providers (contracts); source of flex (EV, water cylinder, battery, C&I etc), purpose (reserves, congestion or outage management, spot/network charge avoidance); capacity (MW); and flex used.
  the data has not yet been analysed / used.
Actions: Ask the EA observer to report back on options to quickly produce flex metrics using retailer flex data.
Notes: Flex Day 2026 identified 8 potential actions to support more effective learning-by-doing by enabling more structured knowledge sharing and coordinated solutions to common project design issues. For avoidance of doubt, these actions are critical to accelerated flex progress.
#1 Develop a generic project component guide including key elements/tasks, handy resources and practice/choices for other projects. FF resources not sufficient to do this. Not aware of any structured effort on this action.
#2 Support/facilitate retailer involvement in flex-y projects, initially by identifying barriers to participating. This should be an output of proposed support to EECA (see item 2 and this item - supporting learning-by-doing update). Not aware of any structured effort underway on this action.
#3 Support/facilitate identification of common flex-y project elements, and assist with standardisation. Focus of fortnightly distributor catch-ups which are coordinated by EECA/Vector.
#4 Support/facilitate regular distributor interaction/co-design sessions for flex-y projects (particularly the scale DF pilot projects). Fortnightly catch-ups of distributors involved in the scale DF pilots are underway using FNF and distributor (Vector) resources. Only indirect FF involvement to date.
#5 to develop a series of think pieces on pricing and orchestration mechanisms needed across the supply chain to activate flex-y propositions… See this item Deep dive update.
#6 to establish a functional knowledge hub… done. Launched 25 November. We are adding more content/updating the blurbs.
#7 to provide quarterly flex-y project status updates will become a BAU FF activity. The first update was provided in the December newsletter. Further updates are being developed, but slowly due to availability of project doers and of FF resources available to curate updates.
#8 to develop a suite of flexibility progress measures and data requirements is within scope of the Framework progress reporting activities. FF, the framework secretariat and Transpower have developed an initial one-off snapshot for the 6 March ETF meeting.

## Slide 11: 4 Workplan (2)
Deep dives. These provide the foundation for FF advice about priorities/dead-ends etc for learning-by-doing and regulatory action for critical topics/issues by filling obvious gaps in understanding of the problems/opportunities.
FF Members have decided that the two most pressing gaps are Digitalisation and Pricing/orchestration.
Deep dive into the ‘digitalisation and data’ snake pit. Very little progress since December with focus during January on Pricing and orchestration mechanisms and arranging workshops
FF member input, corroborated by UK digitalisation plan, provided a sound foundation for a FF perspective… the availability of this was discussed with the EA.
A draft FF insights could be delivered with 10 days focused effort.
Deep dive on pricing and orchestration mechanisms… This note happened in January. It provides the context for a project to consider and identify a suite of pricing and physical orchestration mechanisms to practically support and enable a smart, flexible power system. It was shared with a selection of FF members and the EA on 5 February.
the topic is a top priority of FF Members (action #5 from Flex Day 2026 - see notes page for details), and this has been reiterated in comments at FF workshops so far this year (Powerco, Transpower etc). Unless the issues/questions in the note are addressed, we cannot be confident that practical solutions being developed are robust or enduring.
FF resources are not sufficient to progress this task. See item 2 for discussion of delivery/resourcing options.
Knowledge sharing. Information and updates on flex-y activity are: not regularly shared (if at all); scattered across many websites; and provide varying levels of detail. FF Members very much want more current information on who is doing what.
the Knowledge Hub is slowly growing… curation requires time/effort
3 flex project updates were published to the KH 12/25 and work is underway for an update on the Queenstown electrification accelerator project. Updates will be produced regularly as info becomes available.
  note: information was requested 12/25 for updates on the Scaled DF projects, but holidays etc delayed progress
monthly lunchtime sessions kicked off 04/02 with Rewiring Aotearoa. Next up are: 4 March… Zohreh Saliman, PHD student, University of Auckland will share the cost-benefit analysis of multiple trading relationships arrangements; and 1 April… James Tipping, GM, Vector will share what Vector is thinking and doing to provide more accurate pricing signals options
an occasional webinar series with international experts is being organised…
Flex Day 2026… initial thinking on time, place and theme = September or October in Wellington or Auckland focusing on practical experience (field trips?).

## Slide 12: 4 Workplan (3)
Support for learning-by-doing. FF is uniquely placed to enhance collaboration/synergies by joining dots between the diverse range of actors undertaking learning-by-doing. Activities include:
occasional one-off workshops on behalf of a member(s) to streamline information/feedback gathering or concept testing etc, eg, workshop hosted for Transpower WBOP team.
series of workshops on topics relevant to flex project design/delivery, and particularly inter-dependent issues/questions. See item 2 for discussion of request from EECA.
active ‘brokering’ of cross-sector input to/participation in learning-by-doing, eg, supporting structured retailer/distributor interactions. See item 2 for discussion of request from EECA.
supporting research coordination/collaboration to achieve: a standard research data set; more data sharing (for related/follow on research); greater sharing of research expertise; and minimising research duplication (and research gaps). Initial discussions had with Ara Ake, university Members and EECA.

## Slide 13: 5 Finance update (1)
Purpose of this item:
note budget v actual performance for 2025
note status of membership renewals
approve proposed budget allocations for 2026
Actions: approve the proposed budget allocation for 2026

## Slide 14: 6 Membership requests
Purpose of this item:
note Membership enquiries, requests and decisions since previous meeting
Membership requests and decisions
none received since December SG meeting
Actions: none requested

## Slide 15: 7 Actions
Purpose of this item:
Note actions
Actions from FlexForum and Steering Group meetings from 1 July 2023 to 31 December 2025 are documented here: FF collated actions - FF and SG meetings
all time-bound and time-critical actions are complete or underway
Actions: No action requested

## Slide 16: 8 Next meeting
Purpose of this item:
confirm the date for the next Steering Group meeting
Next Steering Group meeting. The next SG meeting is Thursday 12 March 2026.
ACTION: confirm the date for the next SG meeting.

## Slide 17: 9 Other business
Purpose of this item:
Other business